## Sheet1
Task Id | Task Description | Start Date | End Date | Resources | Dependancy | Comments | Status
1 | Update Business locator data extract spreadsheet with new site id and facility type and add any missing sites | 2012-11-05 | 2012-11-09 | Brian T, Rosi, Sridhar |  | Use Chris Hubbard's spreadsheet
2 | Add a new attribute called Locator Site Id and Facility Type and upload the spreadsheet (Dev environment) | 2012-11-12 | 2012-11-16 | Sridhar |  | Use Brian T's updated spreadsheet
3 | Loading of RS 513 in Prod - confrimed |  |  | Ajith |  |  | Complete
4 | Confirm that Lawson-zipcode job from BI skips manual overridden records and correction to setting of active/ inactive status flags of division (it was incorrectly setting these flags) | 2012-11-10 | 2012-11-10 | Ajith |  |  | Complete
5 | Automated Load org_corp_hier in Prod (do not update site name ..these are manually updated) and audit columns in the hierarchy table - in Dev environment | 2012-11-06 | 2012-12-31 | Sridhar |  | Design complete by 11/9/12
6 | Change the views so that End date is taken into account at the rigth levels - 8 views | 2012-11-19 | 2012-11-30 | Sridhar |  |  | Complete
7 | Add attributes to sites for handling user info like NA Coordinator - Thomas needs to provide the list of the roles to Ajith | 2012-11-06 | 2012-11-09 | Sridhar |  |  | Complete
8 | Region table - Either end date existing regions and add 4 new regions if the name changes. If region names do not change, keep the four and end date one region. |  |  |  |  | Check with Narrio how BI is going to handle this. | Complete
9 | Area Table - Update region id (Pk of region table) for the areas that exist and end date the ones that do not exist. OR if these are all new areas, then end date all the existing areas and add the new ones. | [5 empty] | Complete
10 | BU Table - Should we add Area id to the BU table ? Update the area id in this table. No end date of BU since no change in BU is expected. | [5 empty] | Complete
11 | Division Table - Update the area id in the Division table and end date the ones that do not come through as valid divisions from BI | [5 empty] | Complete
12 | Tables for competitor info, 3rd party info etc |  | 2012-11-30 | Thomas, Ajith
13 | Wireframes for all data entry screens | 2012-11-28 | 2012-12-03 | Rosi, Thomas |  |  | Complete
14 | Validate design document with Requirements document | 2012-11-28 | 2012-12-03 | Thomas, Rosi
15 | WSDL (stubs) |  | 2012-12-06 | Kurt, Thomas |  |  | Complete
16 | UI - Main form |  | 2012-12-11 | Suresh |  |  | Complete
17 | UI - Tab form |  | 2012-12-21 | Suresh |  | Waiting for updated wireframes from Thomas | Complete
18 | Create project in TFS |  | 2012-12-06 | Thomas |  |  | Complete
19 | Develop class objects |  | 2012-12-10 | Thomas |  |  | Complete
20 | UI updates |  | 2012-01-05 | Suresh
21 | Site Status - how is this being handled correctly and identify corrective actions |  | 2012-12-31 | Thomas, Shakir, Sridhar |  |  | Complete
22 | Only show SearchResults grid when Search button has been pressed and results are found. Otherwise, just show message: "No Results Found" |  | 2012-12-31 | Suresh |  |  | Complete
23 | Search Webpart - Wire filling of State, Region, Area and Business Unit drop downs to WebService call to SRAZPHX074 |  | 2012-12-31 | Suresh |  |  | Complete
24 | Search Webpart - Wire Search button click to WebService call to SRAZPHX074 (GetFilteredSites) |  | 2012-12-31 | Suresh |  |  | Complete
25 | Search Webpart - Wire SiteID link click (in SearchResult grid) to WebService call to SRAZPHX074 (GetSite) |  | 2012-12-31 | Suresh |  |  | Complete
26 | Faculty Info Webpart - Rename Tab to Facility Information |  | 2012-12-31 | Suresh |  |  | Complete
27 | Faculty Info Webpart - Only show last 5 tabs if Facility Type is Transfer |  | 2012-12-31 | Suresh |  |  | Complete
28 | Faculty Info Webpart - Only show WebPart if SiteID selected in SearchResults grid |  | 2012-12-31 | Suresh |  |  | Complete
29 | Display Modal Edit window with 5 input fields when Edit button Faculty Info Webpart - pressed on Facility Information. |  | 2012-12-31 | Suresh |  |  | Complete
30 | Wire filling of State, Region, Area and Business Unit drop downs to Faculty Info Webpart - WebService call to SRAZPHX074 |  | 2012-12-31 | Suresh |  |  | Complete
31 | Others - Rearrange WebParts to be more zone restricted (Middle, footer, etc) |  | 2012-01-05 | Suresh
32 | LocationServices - GetSite |  | 2012-12-31 | Kurt
33 | LocationServices - GetFilteredSites |  | 2012-12-31 | Kurt
34 | MaintenanceServices - GetActiveDivisions |  | 2012-12-31 | Kurt |  |  | Complete
35 | MaintenanceServices - GetActiveArea |  | 2012-12-31 | Kurt |  |  | Complete
36 | MaintenanceServices - GetActiveBusinessUnits |  | 2012-12-31 | Kurt |  |  | Complete
37 | MaintenanceServices - GetActiveDivisions |  | 2012-12-31 | Kurt |  |  | Complete
38 | MaintenanceServices - GetActiveRegions |  | 2012-12-31 | Kurt |  |  | Complete
39 | MaintenanceServices - GetActiveStatuses |  | 2012-12-31 | Kurt
40 | MaintenanceServices - GetActivePropertyTypes |  | 2012-12-31 | Kurt |  |  | Complete
41 | DB Model Import |  | 2012-12-17 | Kurt |  |  | Complete
42 | MaintenanceServices - UpdateSiteDivisionalInfo |  | 2012-12-31 | Kurt
43 | MaintenanceServices - CreateSiteInfo |  | 2012-12-31 | Kurt
44 | MaintenanceServices - UpdateSiteAddressInfo |  | 2012-12-31 | Kurt
45 | MaintenanceServices - CreateSiteAddressInfo |  | 2012-12-31 | Kurt
46 | MaintenanceServices - UpdateSiteServiceCapabilityInfo |  | 2012-12-31 | Kurt
47 | MaintenanceServices - GetSitesWithLawsonNo |  | 2012-12-31 | Kurt
48 | LocationServices- GetInternalPostCollectionFacilities |  | 2012-12-31 | Kurt
49 | MaintenanceServices - CreateInternalPostCollectionFacilities |  | 2012-12-31 | Kurt
50 | MaintenanceServices - UpdateInternalPostCollectionFacilities |  | 2012-12-31 | Kurt
51 | MaintenanceServices - DeleteInternalPostCollectionFacilities |  | 2012-12-31 | Kurt
52 | LocationServices- Get3rdPartyPostCollectionFacilities |  | 2012-12-31 | Kurt
53 | MaintenanceServices - Create3rdPartyPostCollectionFacilities |  | 2012-12-31 | Kurt
54 | MaintenanceServices - Update3rdPartyPostCollectionFacilities |  | 2012-12-31 | Kurt
55 | MaintenanceServices - Delete3rdPartyPostCollectionFacilities |  | 2012-12-31 | Kurt
56 | LocationServices- GetCollectionCompetitors |  | 2012-12-31 | Kurt
57 | MaintenanceServices - CreateCollectionCompetitor |  | 2012-12-31 | Kurt
58 | MaintenanceServices - UpdateCollectionCompetitor |  | 2012-12-31 | Kurt
59 | MaintenanceServices - DeleteCollectionCompetitor |  | 2012-12-31 | Kurt
60 | LocationServices- GetFranchiseAreasInternal |  | 2012-12-31 | Kurt
61 | MaintenanceServices - CreateFranchiseAreasInternal |  | 2012-12-31 | Kurt
62 | MaintenanceServices - UpdateFranchiseAreasInternal |  | 2012-12-31 | Kurt
63 | MaintenanceServices - DeleteFranchiseAreasInternal |  | 2012-12-31 | Kurt
64 | LocationServices- GetFranchiseAreasCompetitor |  | 2012-12-31 | Kurt
65 | MaintenanceServices - CreateFranchiseAreasCompetitor |  | 2012-12-31 | Kurt
66 | MaintenanceServices - UpdateFranchiseAreasCompetitor |  | 2012-12-31 | Kurt
67 | MaintenanceServices - DeleteFranchiseAreasCompetitor |  | 2012-12-31 | Kurt
68 | LocationServices- GetSiteManagementContactInfo |  | 2012-12-31 | Kurt
69 | StoredProcedures - USP_ServiceLocator_GetStates |  | 2012-12-31 | Shakir |  |  | Complete
70 | StoredProcedures - USP_ServiceLocator_GetRegions |  | 2012-12-31 | Shakir |  |  | Complete
71 | StoredProcedures - USP_ServiceLocator_GetAreas |  | 2012-12-31 | Shakir |  |  | Complete
72 | StoredProcedures - USP_ServiceLocator_GetBusinessUnits |  | 2012-12-31 | Shakir |  |  | Complete
73 | StoredProcedures - USP_ServiceLocator_GetDivisions |  | 2012-12-31 | Shakir |  |  | Complete
74 | StoredProcedures - USP_ServiceLocator_GetSites |  | 2012-12-31 | Shakir
75 | StoredProcedures - USP_ServiceLocator_GetSite |  | 2012-12-31 | Shakir
76 | StoredProcedures - USP_ServiceLocator_GetPropertyTypes |  | 2012-12-31 | Shakir
77 | StoredProcedures - USP_ServiceLocator_UpdateDivisionalInfo |  | 2012-12-31 | Shakir
78 | StoredProcedures - USP_ServiceLocator_CreateSite |  | 2012-12-31 | Shakir
79 | StoredProcedures - USP_ServiceLocator_UpdateSiteAddressInfo |  | 2012-12-31 | Shakir
80 | StoredProcedures - USP_ServiceLocator_CreateSiteAddressInfo |  | 2012-12-31 | Shakir
81 | StoredProcedures - USP_ServiceLocator_UpdateServiceCapabilityInfo |  | 2012-12-31 | Shakir
82 | StoredProcedures - USP_ServiceLocator_GetSitesWithLawsonNo |  | 2012-12-31 | Shakir
83 | StoredProcedures - USP_ServiceLocator_GetInternalPostCollectionFacilities |  | 2012-12-31 | Shakir
84 | StoredProcedures - USP_ServiceLocator_CreateInternalPostCollectionFacilities |  | 2012-12-31 | Shakir
85 | StoredProcedures - USP_ServiceLocator_UpdateInternalPostCollectionFacilities |  | 2012-12-31 | Shakir
86 | StoredProcedures - USP_ServiceLocator_DeleteInternalPostCollectionFacilities |  | 2012-12-31 | Shakir
87 | StoredProcedures - USP_ServiceLocator_Get3rdPartyPostCollectionFacilities |  | 2012-12-31 | Shakir
88 | StoredProcedures - USP_ServiceLocator_Create3rdPartyPostCollectionFacilities |  | 2012-12-31 | Shakir
89 | StoredProcedures - USP_ServiceLocator_Update3rdPartyPostCollectionFacilities |  | 2012-12-31 | Shakir
90 | StoredProcedures - USP_ServiceLocator_Delete3rdPartyPostCollectionFacilities |  | 2012-12-31 | Shakir
91 | StoredProcedures - USP_ServiceLocator_GetCollectionCompetitors |  | 2012-12-31 | Shakir
92 | StoredProcedures - USP_ServiceLocator_CreateCollectionCompetitors |  | 2012-12-31 | Shakir
93 | StoredProcedures - USP_ServiceLocator_UpdateCollectionCompetitors |  | 2012-12-31 | Shakir
94 | StoredProcedures - USP_ServiceLocator_DeleteCollectionCompetitors |  | 2012-12-31 | Shakir
95 | StoredProcedures - USP_ServiceLocator_GetFranchiseAreasInternal |  | 2012-12-31 | Shakir
96 | StoredProcedures - USP_ServiceLocator_CreateFranchiseAreasInternal |  | 2012-12-31 | Shakir
97 | StoredProcedures - USP_ServiceLocator_UpdateFranchiseAreasInternal |  | 2012-12-31 | Shakir
98 | StoredProcedures - USP_ServiceLocator_DeleteFranchiseAreasInternal |  | 2012-12-31 | Shakir
99 | StoredProcedures - USP_ServiceLocator_GetFranchiseAreasCompetitor |  | 2012-12-31 | Shakir
100 | StoredProcedures - USP_ServiceLocator_CreateFranchiseAreasCompetitor |  | 2012-12-31 | Shakir
101 | StoredProcedures - USP_ServiceLocator_UpdateFranchiseAreasCompetitor |  | 2012-12-31 | Shakir
102 | StoredProcedures - USP_ServiceLocator_DeleteFranchiseAreasCompetitor |  | 2012-12-31 | Shakir
103 | StoredProcedures - USP_ServiceLocator_GetSiteManagementContactInfo |  | 2012-12-31 | Shakir
104 | Documentation - Requirements Checklist |  | 2012-12-31 | Thomas
105 | Documentation - Final Rewrite/Merge |  | 2012-12-31 | Thomas
106 | Documentation - Project DBScript Repository |  | 2012-12-31 | Thomas
107 | Documentation - WSDL Cleanup on WebServices |  | 2012-12-31 | Thomas
108 | Database model improt into Erwin |  | 2013-01-05 | Sridhar
109 | Integrated unit testing |  | 2013-01-05 | Thomas, Kurt, Shakir
110 | Confirm the documentation template and details to ensure it matches with TIBCO process |  | 2013-01-12 | Thomas
111 | Identify and create the AD groups to be used |  | 2013-01-04 | Rosi, Lorenzo |  |  |  | Testing dependancy
112 | Keep Requirements updated |  | 2013-01-12 | Rosi
113 | Waste disposition rule |  | 2012-12-31 | Rosi
114 | Info Webpart - Facility Information Tab - UI/View/Edit | 2012-12-10 | 2013-01-05 | Suresh |  | Dependency with WebMethods
115 | Info Webpart - Address Tab - UI/Create/Edit/Delete | 2012-12-10 | 2013-01-05 | Suresh |  | Dependency with WebMethods
116 | Info Webpart - Services Tab - UI/View/Edit | 2012-12-10 | 2013-01-05 | Suresh |  | Dependency with WebMethods
117 | Info Webpart - Post Collection Information Tab - UI/Create/Edit/Delete | 2012-12-10 | 2013-01-05 | Suresh |  | Dependency with WebMethods
118 | Info Webpart - 3rd Party Collection Information Tab - UI/Create/Edit/Delete | 2012-12-10 | 2013-01-05 | Suresh |  | Dependency with WebMethods
119 | Info Webpart - Collection Competitor Information Tab - UI/Create/Edit/Delete | 2012-12-10 | 2013-01-05 | Suresh |  | Dependency with WebMethods
120 | Info Webpart - Franchise Internal Tab - UI/Create/Edit/Delete | 2012-12-10 | 2013-01-05 | Suresh |  | Dependency with WebMethods
121 | Info Webpart - Franchise Competitor Tab - UI/Create/Edit/Delete | 2012-12-10 | 2013-01-05 | Suresh |  | Dependency with WebMethods